## Sheet1
Project Name: | Telco Customer Churn Prediction
Report Date: | 2026-09-21
[5 empty] | Milestone #1 |  |  |  | Milestone #2 |  |  |  | Milestone #3
Deliverable | Tasks | Complete% | Current Status Memo | Assigned To | 2026-08-30 | 2026-09-06 | 2026-09-13 | 2026-09-20 | 2026-09-27 | 2026-10-04 | 2026-10-11 | 2026-10-18 | 2026-10-25 | 2026-11-01 | 2026-11-08 | 2026-11-15 | 2026-11-22 | 2026-11-29
Project Planning & Governance | Project Plan | 100% | Completed | Joshua Chuhran & Salman Baig | 2026-09-06: 3; 2026-09-20: 3
| GitHub Repository Setup | 100% | Completed | Joshua Chuhran | 2026-09-20: 3
| Gantt Chart & Workload Planning | 100% | Completed | Joshua Chuhran | 2026-09-20: 3
| Milestone 1 Powerpoint Presentation | 100% | Completed | Salman Baig | 2026-09-20: 3
| Milestone 1 Submission Review | 100% | Completed | Salman Baig, Joshua Chuhran, Marshall Marlow, Alex Clark | 2026-09-20: 3
| Milestone #1 Submission | 100% | Completed | Joshua Chuhran | 2026-09-20: 0
Data Engineering & EDA | Kaggle Dataset Acquisition & Cleaning | 100% | Completed | Salman Baig | 2026-09-06: 3
| Exploratory Data Analysis (EDA) | 0% | Not Started | Alex Clark
| Data Cleaning & Preprocessing Pipeline | 0% | Not Started | Alex Clark
| Feature Engineering & Selection | 0% | Not Started | Marshall Marlow
Predictive Modeling & Evaluation | Baseline Model Implementation | 0% | Not Started | Doris Onyeanula
| Milestone #2 Submission | 0% | Not Started | Joshua Chuhran
| Advanced Model Tuning (Random Forest / XGBoost) | 0% | Not Started | Salman Baig
| Model Evaluation (F1-Score & PR-AUC) | 0% | Not Started | Marshall Marlow
| Milestone #3 Submission | 0% | Not Started | Joshua Chuhran
Results Analysis & Final Documentation | Model Results Visualization & Insights | 0% | Not Started | Doris Onyeanula
| GitHub Website & Documentation Finalization | 0% | Not Started | Alex Clark
| Final Slide Deck & Presentation Prep | 0% | Not Started | Salman Baig
| Final Project Deliverables Submission | 0% | Not Started | Marshall Marlow
| Total workload | 21 |  |  | 0 | 6 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Legend
Planned
Completed
Number | Workload: man hour