## Slide 1
IT4793 CAPSTONE · MILESTONE 1 PROGRESS
Telco Customer Churn Prediction
Predicting at-risk customers with machine learning to protect recurring revenue
Joshua Chuhran · Doris Onyeanula · Alex Clark · Salman Baig · Marshall Marlow
Kennesaw State University · College of Computing and Software Engineering · Fall 2026

## Slide 2
Project Overview
Customer churn — when a subscriber cancels service — directly erodes recurring telecom revenue. This project builds a predictive analytics pipeline that flags at-risk customers early, so retention teams can intervene before they leave.
Data source: Kaggle Telco Customer Churn dataset (IBM), covering customer demographics, account tenure, and subscribed services.
7,000+
customer records
3
ML models planned
2
success metrics
Analytical Approach
Logistic Regression, Random Forest, XGBoost
Evaluated on F1-Score & PR-AUC
Python: Pandas, NumPy, Scikit-Learn
Jupyter Notebooks + GitHub version control
Telco Customer Churn Prediction | Milestone 1
2

## Slide 3
Project Team & Roles
JC
Joshua Chuhran
Team Leader & Project Management
DO
Doris Onyeanula
Data Acquisition & Results Visualization
AC
Alex Clark
Exploratory Data Analysis & Documentation
SB
Salman Baig
Preprocessing & ML Model Tuning
MM
Marshall Marlow
Feature Engineering & Model Evaluation
Advisor: Arindam Khanda · Weekly syncs via Microsoft Teams · 24-hour response expectation
Telco Customer Churn Prediction | Milestone 1
3

## Slide 4
Milestone Roadmap
Milestone #1
Sep 25, 2026
Project Plan · Repo Setup · Preliminary Exploration
WE ARE HERE
Milestone #2
Oct 20, 2026
Feature Engineering · Baseline Model · Diagnostics
Milestone #3
Nov 10, 2026
Advanced Tuning · Evaluation (F1 / PR-AUC) · Draft Docs
Telco Customer Churn Prediction | Milestone 1
4

## Slide 5
Progress by Work Area
From the project workload tracker & Gantt chart
Project Planning & Governance
100%
Data Engineering & EDA
17%
Predictive Modeling & Evaluation
0%
Results Analysis & Final Documentation
0%
Milestone 1 Snapshot
Project Plan
Complete
Repo Setup
Complete
Gantt Chart
Complete
Dataset Acquisition
In Progress
Data Exploration
Not Started
Telco Customer Churn Prediction | Milestone 1
5

## Slide 6
Milestone 1 Deliverables
Complete
Project Plan
Scope, team roles, communication plan, and milestone schedule finalized and published to the repo.
Complete
GitHub Repository Setup
Repository structured with Data, Deliverables, and Project_Planning folders; version control active.
Complete
Gantt Chart & Workload Tracker
Task breakdown with owners and weekly hour allocations tracked in the WBS/Gantt document.
In Progress
Preliminary Data Exploration
Kaggle Telco Churn dataset identified; acquisition and initial cleaning underway.
Telco Customer Churn Prediction | Milestone 1
6

## Slide 7
Next Steps Toward Milestone 2
Due October 20, 2026
1
Finish Dataset Acquisition & Cleaning
Salman Baig
2
Exploratory Data Analysis (EDA)
Alex Clark
3
Build Preprocessing Pipeline
Salman Baig
4
Feature Engineering & Selection
Marshall Marlow
5
Implement Baseline Model
Doris Onyeanula
Telco Customer Churn Prediction | Milestone 1
7